## KEY
Item | Meaning
Purpose | Every variable in g.master_data_merged that still needs a decision, a fix, or a documented caveat before analysis. Built 2026-08-27 from the PeCAN merge project record (PCM findings, decisions and traps).
Status: OPEN | Needs a decision. Nobody has determined the right answer yet.
Status: OPEN-PRICE | Needs a decision from Price specifically -- a study-design question, not a data question.
Status: RESOLVED-KEEP | Decided: keep the columns separate. No code change. Downstream users must be told.
Status: FIXED | Already corrected in the pipeline. Listed so the change is visible and traceable.
Status: VERIFY | A specific check would settle it. The query is given in the Action column.
Status: NO ACTION | Listed only so it is not mistakenly grouped with something it resembles.
Priority: HIGH | Could produce a wrong published number if ignored.
Priority: MED | Affects interpretation or completeness, not correctness.
Priority: LOW | Documentation only.
Evidence | Where the claim comes from. PCM-F = finding, PCM-D = decision, PCM-T = trap, MRG/PREP/QC = requirement implemented in code.
Sheets | Duplicate Concepts ¦ Type & Encoding ¦ Data Quality ¦ Coverage & Cohort ¦ Traps
Caution | This register is the project's accumulated knowledge, not a substitute for inspecting the data. Where a row says VERIFY, the check has NOT been run.

## Duplicate Concepts
Variable | Source(s) | Status | Priority | Issue | Evidence | Action
Death_Date_Y_N | md1-md5 | RESOLVED-KEEP | HIGH | Mortality flag under three names across sources. Plausibly one concept; never verified as distinct. | PCM-D-01 | Kept as three columns. Any mortality analysis must decide which applies to which patients -- in_md1..in_md8 make that determinable. Record in the data dictionary.
IsDead_Y_N | md6 | RESOLVED-KEEP | HIGH | Same concept as Death_Date_Y_N and Death, most likely. | PCM-D-01 | As above. Cross-tab against Death_Date_Y_N on the md6 overlap to test whether they agree.
Death | md7 | RESOLVED-KEEP | HIGH | Same concept as Death_Date_Y_N and IsDead_Y_N, most likely. | PCM-D-01 | As above.
_30_DAY_MORTALITY | md1, md2 | NO ACTION | LOW | A DIFFERENT measure from the death flags -- time-bounded. Never a merge candidate. | PCM-D-01 | No action. Listed so it is not mistakenly folded in with the death flags.
Death_Days_After_Surgery | md-various | NO ACTION | LOW | A third distinct measure -- interval, not a flag. | PCM-D-01 | No action.
Feels_Exausted, Low_Physical_Activity, Slow_Walking_Speed, Unintended_Weight_Loss, Week_Grip_Strength | md6, md7 | RESOLVED-KEEP | MED | Five frailty items as CHARACTER Y/N. md7 stores $3, md6 stores $1 -- the width difference is itself evidence the encodings are not interchangeable. | PCM-D-02, MRG-04 | Kept. md7 owns these via an explicit override (md6 wins on row count but cannot hold 3-character values). Do not assume a clean mapping to the _Value columns.
Feels_Exausted_Value, Low_Physical_Activity_Value, Slow_Walking_Speed_Value, Unintended_Weight_Loss_Value, Week_Grip_Strength_Value | md3, md5 | RESOLVED-KEEP | MED | The same five frailty items as NUMERIC. Ten columns for five concepts. | PCM-D-02 | Kept. VERIFY whether the numeric and character forms encode the same thing before using either.
ISO_SEV_Exp_IntraOp_MAC_Average | md1-md3 | OPEN | MED | Likely the same measure as md4's ISO_SEV_IntraOp_MAC_Average -- a naming variant. | PCM-D-03 | VERIFY: cross-tab against the md4 column on overlapping patients. If they agree, one column is redundant.
ISO_SEV_IntraOp_MAC_Average | md4 | OPEN | MED | Likely a naming variant of the md1-md3 column. | PCM-D-03 | As above.
ISO_SEV_MAC_TOTAL_Exp | md8 | RESOLVED-KEEP | MED | Says TOTAL where the others say AVERAGE. Genuinely a different statistic. | PCM-D-03 | Keep separate permanently. Do NOT fold into the average columns even if D-03 resolves the other two.
Sleep_Apnea / Sleep_Apnea_YN | md4-md5 / md3 | VERIFY | MED | Naming variant of the same comorbidity flag, almost certainly. | Phase 2 ownership map | VERIFY: compare on overlapping patients. If identical, collapse to one column and document.
Diabetes / Diabetes_YN | md4-md5 / md3 | VERIFY | MED | As above. | Phase 2 ownership map | As above.
Hyperlipidemia / Hyperlipidemia_YN | md4-md5 / md3 | VERIFY | MED | As above. | Phase 2 ownership map | As above.
Hypertension / Hypertension_YN | md4-md5 / md3 | VERIFY | MED | As above. | Phase 2 ownership map | As above.
MovementDisorder / MovementDisorder_YN | md4-md5 / md3 | VERIFY | MED | As above. | Phase 2 ownership map | As above.
Cognitive_Disorder / CognitiveDisorder_YN | md4-md5 / md3 | VERIFY | MED | As above. | Phase 2 ownership map | As above.
Cognitive_Score / Cognitive_Category | md3 + md8 | VERIFY | MED | Score is 0-3; Category is a $22 label. Almost certainly the same assessment at two granularities. | Phase 9 / recovery sweep | VERIFY: proc freq Cognitive_Score * Cognitive_Category / list missing. A clean one-to-many mapping means Category is derivable and redundant.
Frailty_Score / Frailty_Category | md3 + md8 | VERIFY | MED | Score is 0-5 (Fried phenotype); Category is a label. Same question as the cognitive pair. | Phase 9 / recovery sweep | VERIFY: proc freq Frailty_Score * Frailty_Category / list missing.
PRECEDE_Study_ID_1 | md6 | FIXED | LOW | Duplicate of PRECEDE_STUDY_ID in md6. | PCM-D-06, PREP-04 | Dropped in Phase 3, after asserting it was identical to the key in every row. Not in the merged file.

## Type & Encoding
Variable | Where | Status | Priority | Issue | Evidence | Action
Admit_BMI | md8 vs md1-md7 | FIXED | HIGH | CHAR $11 in md8, NUMERIC elsewhere -- md8 stored the literal string NULL as a sentinel. | PCM-F-05, PREP-03 | Converted to numeric in Phase 3 with a measured exception report.
ASA__Anesth_Record_ | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
Age_at_Encounter | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
Cognitive_Score | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
Frailty_Score | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
rt_INCISE_to_DRESS_mins | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
rt_RM_START_to_INCISION_mins | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
rt_RM_START_to_RM_END_mins | md8 | FIXED | HIGH | CHAR in md8, NUMERIC elsewhere. | PREP-03 | Converted in Phase 3.
Base_Procedure_Code_1 | md4-md7 vs md1-3, md8 | FIXED | HIGH | NUM 8 in md4-md7, CHAR $10 in md1/md2/md3/md8. | PREP-07 | Harmonised to CHARACTER $10 in Phase 3. Converted toward character deliberately -- input() on a code with a leading zero or letter destroys it.
Emergent, Intraop_Ketamine, Preop_block | md8 | FIXED | MED | md8 stored the literal string NULL where other sources store a blank, which forced these to $4. | PCM-F-05, PREP-03 | Sentinel cleared to blank in Phase 3; declared $1 in the merged file.
Base_Procedure_1 | all | OPEN | LOW | Encoding damage on esophagectomy descriptions -- ESOPH? instead of ESOPH-. Session encoding is not UTF-8. | PCM-F-10, PCM-C-01 | Counted and reported per source, values left untouched. Fewer than 9 rows per file. Decide whether to re-extract or annotate.
OWN-04 coalesce check | Phase 2 | OPEN | MED | Phase 2 reads RAW sources, where md8's converted numerics are still character, so every md3-md8 comparison for the eight PREP-03 targets is skipped. | Observed 2026-08-27 | Structural limitation: OWN-04 cannot check the variables most at risk. 03b_recover_sweep.sas answers the question instead. Record the limitation in DECISIONS.md.

## Data Quality
Variable | Status | Priority | Affected rows | Issue | Evidence | Action
rt_INCISE_to_DRESS_mins | FIXED | HIGH | 52 | 52 NEGATIVE values -- dressing timestamp before incision. Max is -1; 75% sit between -6.5 and -1. Concentrated in percutaneous services (46% Neurosurgery, 20% EP/interventional cardiology) where there is no incision or dressing in the surgical sense. | PCM-F-13, PCM-F-14, PREP-08 | Set to missing at source in Phase 3.
rt_RM_START_to_INCISION_mins | FIXED | HIGH | 15 | 15 NEGATIVE values. Disjoint from the 52 above, so 67 distinct rows are affected. | PCM-F-13, PREP-08 | Set to missing at source in Phase 3.
rt_INCISE_to_DRESS_mins / rt_RM_START_to_INCISION_mins | RESOLVED-KEEP | HIGH | 9 | 9 rows where a sub-interval EXCEEDS the room-occupancy interval containing it (5 + 4). All values POSITIVE and inside the old QC-05 bounds, so a range check cannot see them. | PCM-F-15, PCM-D-08, MRG-05 | FLAGGED, not nulled -- rt_envelope_flag = 1. Each timestamp is individually plausible and nothing identifies which of the three is wrong; nulling would destroy two good values to punish one bad one. QC-06 asserts zero UNFLAGGED violations.
rt_RM_START_to_AN_START_mins | OPEN | HIGH | 22,575 in md3 | NEGATIVE on 50-62% of rows in EVERY source. This is not error -- anesthesia routinely starts before OR entry, in pre-op holding or an induction room. The rt_RM_START_to_* family are OFFSETS from room start, not durations. | PCM-D-10, PREP-09 | Do NOT null. Anyone computing 'time from room entry to anesthesia start' as a duration gets systematically wrong results on half the cohort. Rename or document prominently.
rt_RM_START_to_INDUCTION_mins | OPEN | MED | 29 in md3 | Small negative counts, same offset-not-duration reasoning as above. | PREP-09 | Review alongside the AN_START variable. Likely legitimate.
rt_BLOCK_START_TO_BLOCK_END_MINS | OPEN | MED | 1 | 1 negative value in md1/md2/md3. A true duration -- block end before block start is impossible at any scale. | PREP-09 | Genuine error. Decide whether to null it or report upstream. Only one row.
rt_ADMIT_to_* family | OPEN | LOW | 1-4 each | Small negative counts. Plausibly real (a block placed in pre-op before the formal admit timestamp) or plausibly error at these counts. | PREP-09 | Review the PREP-09 report. Low volume either way.
rt_ANCHOR_to_ADMIT_days etc. | RESOLVED-KEEP | LOW | 0 | Zero negatives found. These are offsets from an anchor date where negative would be LEGITIMATE. | PCM-D-10, PREP-09 | No action. PREP-08 deliberately excludes them from nulling -- protection was correct in principle and moot in practice.
Emergent | RESOLVED-KEEP | MED | 7 in md1, 21 in md8 | 0.05% and 0.09% positive at source, with matching blank shares across two independent exports. Consistent with a field clinicians rarely complete rather than a true emergency rate. | PCM-F-06, PCM-D-04 | RETAINED with a caveat. The merged value is md3-owned; see qc/06_reconcile_summary.txt for the observed distribution. Do NOT model on it without checking Patient_Type and Admit_Source first.
Intraop_Ketamine, Preop_block | RESOLVED-KEEP | LOW | n/a | Y-or-blank in every source -- no explicit N anywhere. Blank means 'not given', not 'unknown'. | PCM-F-06 | Derive explicit 0/1 indicators downstream rather than leaving a variable that is never N.

## Coverage & Cohort
Variable | Status | Priority | Numbers | Issue | Evidence | Action
Cognitive_Score | FIXED | HIGH | 12,128 -> 20,540 | md3-owns ownership was DISCARDING 8,412 values md8 held for patients md3 has blanks for. | PCM-F-18, PCM-D-11, MRG-06 | Gap-filled from md8 in Phase 4. Zero disagreements where both sources hold a value.
Cognitive_Category | FIXED | HIGH | +8,445 | Same as above. Found ONLY by sweeping every shared variable -- no spot check would have tested it. | PCM-F-18, MRG-06 | Gap-filled from md8 in Phase 4.
Frailty_Score | FIXED | HIGH | 14,043 -> 23,311 | Same as above -- 9,268 values discarded. | PCM-F-18, MRG-06 | Gap-filled from md8 in Phase 4.
Frailty_Category | FIXED | HIGH | +1,789 | Same as above. Note the asymmetry: md8 has a frailty SCORE for 9,268 patients md3 lacks but a CATEGORY for only 1,789 of them. | PCM-F-18, MRG-06 | Gap-filled. VERIFY whether Category is derivable from Score, which would explain the gap.
ORAL_MORPHINE_EQUIV_mg_POD_DAY6 | VERIFY | MED | +7,695 | Recovers EXACTLY 7,695 -- md4's and md5's row count precisely. A round number matching another source's N usually means structure, not coincidence. | PCM-F-18, MRG-06 | VERIFY BEFORE TRUSTING: proc freq on g.prep_md8. If the values are overwhelmingly a single value (0 especially), it is a default rather than a measurement and coalescing manufactures data.
Admit_BMI | RESOLVED-KEEP | HIGH | 12,726 of 41,150 | 69% missing in the merged file, and coalescing recovers NOTHING from any of the seven other sources including md8. The missing are missing at source. | PCM-F-07, PCM-D-11 | No fix possible. This is the variable that FORCES the cohort restriction: all 12,726 values are inside the admitted cohort, zero outside.
Cognitive_Score / Frailty_Score (cohort) | OPEN-PRICE | HIGH | see note | After MRG-06, 13,288 of 20,540 cognitive and 15,161 of 23,311 frailty scores belong to patients OUTSIDE the admitted cohort. Within the cohort they are the WEAKER variables (52.2% and 58.7%). | PCM-F-19 (supersedes PCM-F-12) | The original cohort rationale is VOID. PCM-F-12 said ambulatory patients were never eligible for the geriatric assessments -- that is now false. Price must re-decide PCM-D-05 on this basis.
Analytic cohort definition | OPEN-PRICE | HIGH | 13,890 admitted | A cognitive/frailty analysis may not want the admitted restriction at all; anything using Admit_BMI has no alternative. | PCM-D-05, PCM-F-19 | Price decision. Blocks Phase 8 DOC-02.
All-three complete-case N | OPEN | HIGH | was 6,523 | The 6,523 figure was measured PRE-coalesce, on a merged file where Cognitive was 12,128 and Frailty 14,043. Both grew by 8-9k. | PCM-F-11 | RE-MEASURE. Phase 7 produces the true value. Do not quote 6,523.
Age_at_Encounter | OPEN | MED | min = 64 | Observed minimum is 64. Either an undocumented upstream inclusion criterion or a filter someone applied. | PCM-D-07 | DEFERRED, not pursued. The QC-05 floor of 18 is a type-sanity guard and CANNOT fire -- do NOT tighten it to 64, that converts an open question into a pipeline abort. Phase 7 inherits this.
Age_at_Encounter / Patient_Type | VERIFY | MED | 2,395 | 2,395 rows have missing Age AND blank Patient_Type -- the same rows. Suggests a distinct record type rather than scattered missingness. | Phase 7 output | VERIFY: characterise those 2,395 rows before the cohort is fixed.
QC-05 time ceilings | FIXED | LOW | 0 | 2000 and 500 minutes never fired on any of 41,150 rows. Every time failure was a negative. | PCM-F-16, PCM-D-09, QC-07 | REMOVED. A bound that has never fired and cannot fire is not a check -- it is an invitation to widen it later to make a run green. Floors handled by PREP-08, containment by QC-06.

## Traps
ID | What goes wrong | Rule
PCM-T-01 | PROC SQL UPDATE with CATS silently blanked all 9,215 rows of md7's key. The result buffer is the target column's existing length; PROC SQL cannot widen a column. | Prefix operations go in a DATA step with an explicit LENGTH.
PCM-T-02 | data X; set X; replaces the dataset on completion with no undo. Combined with T-01 this destroyed md7. | Always write to a new name. Build in WORK, validate, then promote.
PCM-T-03 | Stack-then-dedup yields exactly 41,150 rows and looks correct. It is not -- it discards md8's hemodynamic block entirely. Row count alone does not validate a merge. | Merge on the spine, never stack overlapping variable sets.
PCM-T-05 | In a MERGE, a later dataset overwrites an earlier one EVEN WITH A MISSING VALUE, silently. | KEEP= only what each source owns, so a non-owner copy never enters the PDV.
PCM-T-11 | An unguarded comparison counts missings as negatives: sum(var < 0) returned 8,369 instead of 52, because missing is less than any number in SAS. | Every numeric comparison carries an IS NOT MISSING guard, including throwaway diagnostics.
PCM-T-12 | Spot checks answered the md3-owns question WRONG TWICE. Cognitive_Category and Frailty_Category surfaced only from sweeping every shared variable. | For 'does X hold data Y is discarding', enumerate every candidate. Sweep, do not sample.
PCM-T-13 | dictionary.columns.TYPE is CHARACTER (char/num); PROC CONTENTS OUT= TYPE is NUMERIC (1=num, 2=char). Both appear in this pipeline. | Comparing the dictionary form against 2 silently never matches and sends every variable down the wrong branch.
%PUT hazards | An apostrophe in %PUT text opens a string that never closes and swallows every following statement. A semicolon inside %PUT text ends it early, leaving an orphan statement. | Tell: 'quoted string ... more than 262 bytes' followed by source echoing with no execution output.
Open-code %IF | In OPEN CODE, %IF/%THEN requires a %DO block. A bare statement after %THEN gives 'Expected %DO not found', then SAS skips forward hunting for %END and swallows the file. | Every gate lives inside a named macro. This once made 99_run_all.sas execute nothing at all.
Local %LET | A bare %LET inside a macro is LOCAL. If the variable is read outside, you get an unresolved reference -- or worse, a silently wrong value where a global of the same name exists. | %GLOBAL anything read outside its setting macro. A FAIL status was once reported as PASS this way.
IS NOT MISSING | PROC SQL / WHERE syntax. In a DATA step IF it is a syntax error. | The DATA-step form is NOT MISSING(x). This has bitten the pipeline three times.
&SQLOBS | Unreliable after CREATE TABLE; not reset by statements producing no output, so a stale value can be read. | Banned project-wide. Use SELECT COUNT(*) INTO :macvar TRIMMED.